## Instructions
Committed cost in construction
9 columns · 6 you enter · 1 drop-downs · 2 calculated · 3 validated by type · formulas and checks run 200 rows down
How to use it
1. | Delete the example rows (grey italics) on the Template sheet, or overwrite them.
2. | Fill in the white columns; pick drop-down columns from their lists.
3. | Leave the shaded columns alone — they are formulas, and they fill in as soon as a row has an entry in any of its first three columns.
4. | Use the filter arrows on the header row to sort and filter.
What each column captures
Column | Type | What goes in it | Check
Scope | Text | Free text. | Text
Cost code | Text | Cost code from your cost code list, matching the estimate and the ERP. | Text
Budget | Amount ($) | The budget for the line, from the estimate plus approved changes. | Must be a number; shown as $
Vendor | Text | Vendor or subcontractor name as it appears in your vendor master. | Text
Committed | Amount ($) | Enter the amount in dollars. | Must be a number; shown as $
Buyout variance | Calculated | Calculated: [Budget] − [Committed] | Formula filled down every row
Invoiced | Amount ($) | Enter the amount in dollars. | Must be a number; shown as $
Remaining committed | Calculated | Calculated: [Committed] − [Invoiced] | Formula filled down every row
Status | Drop-down | Where the item stands; pick from the list so the log can be filtered and counted. Options: Not bought out / Out to bid / Awarded / Contract signed. | Drop-down: Not bought out / Out to bid / Awarded / Contract signed
Guide and worked example |  | https://constructelligence.co/guides/committed-cost/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Committed cost in construction
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Scope | Cost code | Budget | Vendor | Committed | Buyout variance | Invoiced | Remaining committed | Status
Concrete | 03 30 00 | 640000 |  | 612000 |  |  |  | Awarded
Framing | 06 10 00 | 780000 |  | 846000 |  |  |  | Awarded