## Instructions
Construction change order form
A change order form, line by line: what changed and why, each cost item with quantity, unit cost and markup, the schedule impact, and who approved it when.
17 columns · 12 you enter · 3 drop-downs · 2 calculated · 6 validated by type · formulas and checks run 200 rows down
How to use it
1. | Give the change a number and describe it, citing the RFI, directive or drawing revision behind it.
2. | Add one row per cost item — labor, material, equipment, subcontract — with quantity and unit cost.
3. | Set markup to what the contract allows for each cost type; amount calculates.
4. | State the schedule impact in days — leaving it blank can waive a time extension under many contracts.
5. | Submit, and record who approved it and when. Filter Status = Approved for billing.
What each column captures
Column | Type | What goes in it | Check
CO no. | Text | Change order number; every cost line of one change carries the same number. | Text
Date | Date | Date of the entry. | Must be a date
Job | Text | Job number exactly as in your accounting system (e.g. J-1104), so rows join to job cost. | Text
Description of change | Text | What is being added, deleted or changed, with the RFI or directive that started it. | Text
Reason | Drop-down | Why the change exists — it decides who pays. Options: Owner request / Design change / Unforeseen condition / Code requirement / Error or omission. | Drop-down: Owner request / Design change / Unforeseen condition / Code requirement / Error or omission
Cost item | Text | One cost line of the change (e.g. 'plumber labor', 'floor drains'). | Text
Cost type | Drop-down | Labor, material, subcontract, equipment or other. Options: Labor / Material / Equipment / Subcontract / Other. | Drop-down: Labor / Material / Equipment / Subcontract / Other
Quantity | Number | Enter a number. | Must be a number
Unit | Text | Unit of measure (EA, LF, SF, CY, HR, LS). | Text
Unit cost | Amount ($) | Enter the amount in dollars. | Must be a number; shown as $
Cost | Calculated | Calculated: [Quantity] × [Unit cost] | Formula filled down every row
Markup % | Percent | Markup the contract allows on this cost type, 0–100. | Must be 0–100
Amount | Calculated | Calculated: [Cost] × (1 + [Markup %] ÷ 100) | Formula filled down every row
Schedule impact (days) | Number | Calendar days the change adds to the contract time (0 if none). | Must be a number
Status | Drop-down | Where the item stands; pick from the list so the log can be filtered and counted. Options: Draft / Submitted / Approved / Rejected / Void. | Drop-down: Draft / Submitted / Approved / Rejected / Void
Approved by | Text | Name of the person who signed for the owner or GC. | Text
Date approved | Date | Enter the date. | Must be a date
Guide and worked example |  | https://constructelligence.co/templates/change-order-form/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Construction change order form
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
CO no. | Date | Job | Description of change | Reason | Cost item | Cost type | Quantity | Unit | Unit cost | Cost | Markup % | Amount | Schedule impact (days) | Status | Approved by | Date approved
CO-07 | 2026-09-29 | J-1131 | Add 4 floor drains, exam corridor (RFI 23) | Owner request | Plumber labor | Labor | 40 | HR | 92 |  | 15 |  | 2 | Submitted
CO-07 | 2026-09-29 | J-1131 | Add 4 floor drains, exam corridor (RFI 23) | Owner request | Floor drains & trap primers | Material | 4 | EA | 610 |  | 15 |  |  | Submitted
CO-07 | 2026-09-29 | J-1131 | Add 4 floor drains, exam corridor (RFI 23) | Owner request | Saw-cut & patch slab | Subcontract | 1 | LS | 1850 |  | 10 |  |  | Submitted