## Instructions
Construction budget template
A construction budget by cost code: original budget, approved changes, revised budget, committed cost, actual cost to date, cost to complete, forecast at completion and variance.
12 columns · 7 you enter · 1 drop-downs · 4 calculated · 5 validated by type · formulas and checks run 200 rows down
How to use it
1. | Enter each cost code from the estimate with its original budget.
2. | Add approved change orders to Approved changes as they are signed.
3. | Each month, update Committed and Actual to date from accounting.
4. | Estimate Cost to complete for every code — that one judgement drives the forecast.
5. | Sort by Variance: the negative ones are where the job is going over.
What each column captures
Column | Type | What goes in it | Check
Cost code | Text | Cost code from your cost code list, matching the estimate and the ERP. | Text
Description | Text | What the line is, in words the other party will recognise. | Text
Cost type | Drop-down | Labor, material, subcontract, equipment or other. Options: Labor / Material / Equipment / Subcontract / Other. | Drop-down: Labor / Material / Equipment / Subcontract / Other
Original budget | Amount ($) | The budget at award, from the estimate. | Must be a number; shown as $
Approved changes | Amount ($) | Budget added or removed by approved change orders. | Must be a number; shown as $
Revised budget | Calculated | Calculated: [Original budget] + [Approved changes] | Formula filled down every row
Committed | Amount ($) | Subcontracts and purchase orders issued, whether invoiced or not. | Must be a number; shown as $
Actual to date | Amount ($) | Cost posted to the code in accounting. | Must be a number; shown as $
Cost to complete | Amount ($) | What is still to be spent to finish the code — an estimate, updated monthly. | Must be a number; shown as $
Forecast at completion | Calculated | Calculated: [Actual to date] + [Cost to complete] | Formula filled down every row
Variance | Calculated | Calculated: [Revised budget] − [Forecast at completion] | Formula filled down every row
% spent | Calculated | Calculated — actual to date as a share of the revised budget (= IF([Revised budget]=0, blank, [Actual to date] ÷ [Revised budget])) | Formula filled down every row
Guide and worked example |  | https://constructelligence.co/templates/construction-budget-template/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Construction budget template
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Cost code | Description | Cost type | Original budget | Approved changes | Revised budget | Committed | Actual to date | Cost to complete | Forecast at completion | Variance | % spent
03-3000 | Concrete | Subcontract | 205000 | 9000 |  | 196000 | 151000 | 71500
05-1200 | Structural steel | Subcontract | 388000 | 0 |  | 379000 | 122000 | 257000
09-2116 | Drywall & framing | Subcontract | 612000 | 0 |  | 598000 | 64000 | 548000
22-0000 | Plumbing | Subcontract | 186000 | 9400 |  | 195400 | 111800 | 83600
01-5000 | General conditions | Other | 262000 | 0 |  | 40000 | 118000 | 162000