## Instructions
Construction daily report template
A construction daily report: one row per trade per day — weather, crew size and hours, work performed and where, equipment, deliveries, inspections, delays, safety and photos.
18 columns · 15 you enter · 2 drop-downs · 1 calculated · 4 validated by type · formulas and checks run 200 rows down
How to use it
1. | Fill one row per trade on site each day; repeat the date, job and weather on each row.
2. | Enter headcount and hours each; man-hours calculate.
3. | Describe the work performed with locations and quantities — 'hung 1,200 SF board, level 2 east'.
4. | Record every delay with its cause the same day; a delay not written down is hard to claim later.
5. | Filter by trade or date range to answer 'how many man-hours did the drywall sub put on level 2?'.
What each column captures
Column | Type | What goes in it | Check
Date | Date | Date of the entry. | Must be a date
Job | Text | Job number exactly as in your accounting system (e.g. J-1104), so rows join to job cost. | Text
Weather | Drop-down | Conditions that affected the work; pick the one that matters most. Options: Clear / Cloudy / Rain / Snow / Wind / Extreme heat / Extreme cold. | Drop-down: Clear / Cloudy / Rain / Snow / Wind / Extreme heat / Extreme cold
Temp high (°F) | Number | Enter a number. | Must be a number
Trade / company | Text | One row per trade or company on site. | Text
Workers | Number | Headcount for that trade today. | Must be a number
Hours each | Number | Hours worked per worker. | Must be a number
Man-hours | Calculated | Calculated: [Workers] × [Hours each] | Formula filled down every row
Work performed | Text | What was done today, specifically (quantities where possible). | Text
Area | Text | Where it was done. | Text
Equipment on site | Text | Free text. | Text
Deliveries | Text | Free text. | Text
Inspections | Text | Free text. | Text
Delays / issues | Text | Anything that stopped or slowed work, and who caused it — the evidence for a delay claim. | Text
Safety | Drop-down | The most serious safety event for that trade today. Options: None / Near miss / First aid / Recordable. | Drop-down: None / Near miss / First aid / Recordable
Visitors | Text | Free text. | Text
Photos | Text | Photo file names or a link to today's folder. | Text
Reported by | Text | Superintendent or foreman filing the report. | Text
Guide and worked example |  | https://constructelligence.co/templates/construction-daily-report-template/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Construction daily report template
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Date | Job | Weather | Temp high (°F) | Trade / company | Workers | Hours each | Man-hours | Work performed | Area | Equipment on site | Deliveries | Inspections | Delays / issues | Safety | Visitors | Photos | Reported by
2026-10-06 | J-1131 | Clear | 61 | Metro Interiors (drywall) | 8 | 8 |  | Hung 1,200 SF board | Level 2 east | Scissor lift | Board delivery 7:30 |  |  | None |  | 2026-10-06/drywall | Superintendent
2026-10-06 | J-1131 | Clear | 61 | Eastline Plumbing | 3 | 8 |  | Rough-in restrooms 201–204 | Level 2 |  |  |  | Waiting on RFI 31 (wall chase depth) | None |  | 2026-10-06/plumbing | Superintendent
2026-10-06 | J-1131 | Clear | 61 | Voltline Electric | 4 | 6 |  | Pulled feeders to panel 2A | Electrical room 2 | Boom lift |  | Underground electrical — passed | Lift down 2 h; rental replaced | Near miss | Owner's rep | 2026-10-06/electrical | Superintendent