## Instructions
Construction schedule template
A construction schedule as a table: activities with durations in workdays, predecessors, start dates and calculated finish dates, percent complete, status and days late.
13 columns · 9 you enter · 2 drop-downs · 2 calculated · 3 validated by type · formulas and checks run 200 rows down
How to use it
1. | Enter activities in order of work, with an ID, phase, trade and duration in workdays.
2. | Give every activity except the first a predecessor ID, and set its Start to the workday after that predecessor's Finish.
3. | Finish dates calculate from Start and Duration, skipping weekends (add holidays in WORKDAY if you need them).
4. | Each week, update % complete and Status; Days late counts workdays past Finish for anything not complete.
5. | Filter Status ≠ Complete and sort by Finish for the look-ahead.
What each column captures
Column | Type | What goes in it | Check
ID | Text | Activity ID (A100, A110…) — predecessors refer to it. | Text
Phase | Text | Phase of the work (e.g. underground, rough-in, trim). | Text
Activity | Text | The schedule activity or scope of work. | Text
Trade / crew | Text | Who performs the activity. | Text
Duration (workdays) | Number | Working days the activity takes; weekends are skipped by the finish formula. | Must be a number
Predecessor ID | Text | The ID of the activity that has to finish before this one starts. | Text
Start | Date | Planned start — or, once started, the actual start. Use the predecessor's finish + 1 workday. | Must be a date
Finish | Calculated | Calculated — start plus duration in workdays, skipping weekends (= IF([Start]=blank, blank, WORKDAY([Start], [Duration (workdays)] − 1))) | Formula filled down every row
% complete | Percent | Physical percent complete, 0–100, from the field — not cost spent. | Must be 0–100
Status | Drop-down | Where the item stands; pick from the list so the log can be filtered and counted. Options: Not started / In progress / Complete / On hold. | Drop-down: Not started / In progress / Complete / On hold
Milestone? | Drop-down | Yes for dates the owner or contract cares about (dry-in, substantial completion). Options: Yes / No. | Drop-down: Yes / No
Days late | Calculated | Calculated — workdays past the finish date for any activity not complete (= IF(OR([Finish]=blank, [Status]="Complete"), 0, MAX(0, NETWORKDAYS([Finish], TODAY()) − 1))) | Formula filled down every row
Notes | Text | Anything that explains the row; free text. | Text
Guide and worked example |  | https://constructelligence.co/templates/construction-schedule-template/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Construction schedule template
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
ID | Phase | Activity | Trade / crew | Duration (workdays) | Predecessor ID | Start | Finish | % complete | Status | Milestone? | Days late | Notes
A100 | Sitework | Mobilize & layout | Cobalt Builders | 3 |  | 2026-11-02 |  | 100 | Complete | No
A110 | Foundations | Excavate & pour footings | Concrete crew | 12 | A100 | 2026-11-05 |  | 60 | In progress | No
A120 | Structure | Steel erection | Steel subcontractor | 15 | A110 | 2026-11-23 |  | 0 | Not started | No |  | Thanksgiving week
A130 | Envelope | Roofing | Roofing subcontractor | 8 | A120 | 2026-12-14 |  | 0 | Not started | No
A140 | MEP | MEP rough-in, floor 1 | MEP trades | 20 | A120 | 2026-12-14 |  | 0 | Not started | No
M1 | Milestone | Dry-in | Cobalt Builders | 1 | A130 | 2026-12-24 |  | 0 | Not started | Yes |  | Owner milestone
Formulas:
Finish = IF([Start]="","",WORKDAY([Start],[Duration (workdays)]-1))
Finish = IF(COUNTA([ID]:[Activity])=0,"",IF([Start]="","",WORKDAY([Start],[Duration (workdays)]-1)))
Days late = IF(OR([Finish]="",[Status]="Complete"),0,MAX(0,NETWORKDAYS([Finish],TODAY())-1))
Days late = IF(COUNTA([ID]:[Activity])=0,"",IF(OR([Finish]="",[Status]="Complete"),0,MAX(0,NETWORKDAYS([Finish],TODAY())-1)))