## Instructions
Drywall and interiors contractor software
8 columns · 7 you enter · 0 drop-downs · 1 calculated · 5 validated by type · formulas and checks run 200 rows down
How to use it
1. | Delete the example rows (grey italics) on the Template sheet, or overwrite them.
2. | Fill in the white columns; pick drop-down columns from their lists.
3. | Leave the shaded columns alone — they are formulas, and they fill in as soon as a row has an entry in any of its first three columns.
4. | Use the filter arrows on the header row to sort and filter.
What each column captures
Column | Type | What goes in it | Check
Job | Text | Job number exactly as in your accounting system (e.g. J-1104), so rows join to job cost. | Text
Week | Date | Week-ending date. | Must be a date
Activity | Text | The schedule activity or scope of work. | Text
Sq ft installed | Number | Enter a number. | Must be a number
Crew hours | Number | Enter a number. | Must be a number
Labor cost | Amount ($) | Enter the amount in dollars. | Must be a number; shown as $
Labor per sq ft | Calculated | Calculated: [Labor cost] ÷ [Sq ft installed] | Formula filled down every row
Estimate per sq ft | Amount ($) | Enter the amount in dollars. | Must be a number; shown as $
Guide and worked example |  | https://constructelligence.co/software/drywall-contractors/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Drywall and interiors contractor software
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Job | Week | Activity | Sq ft installed | Crew hours | Labor cost | Labor per sq ft | Estimate per sq ft
J-1131 | 2026-10-09 | Hang | 6200 | 140 | 9520 |  | 1.45
J-1131 | 2026-10-09 | Tape & finish | 4100 | 118 | 8024 |  | 1.8