## Instructions
Job cost forecasting
10 columns · 6 you enter · 0 drop-downs · 4 calculated · 4 validated by type · formulas and checks run 200 rows down
How to use it
1. | Delete the example rows (grey italics) on the Template sheet, or overwrite them.
2. | Fill in the white columns; pick drop-down columns from their lists.
3. | Leave the shaded columns alone — they are formulas, and they fill in as soon as a row has an entry in any of its first three columns.
4. | Use the filter arrows on the header row to sort and filter.
What each column captures
Column | Type | What goes in it | Check
Job | Text | Job number exactly as in your accounting system (e.g. J-1104), so rows join to job cost. | Text
Cost type | Text | Labor, material, subcontract, equipment or other. | Text
Budget | Amount ($) | The budget for the line, from the estimate plus approved changes. | Must be a number; shown as $
Cost to date | Amount ($) | Enter the amount in dollars. | Must be a number; shown as $
Committed not invoiced | Amount ($) | Enter the amount in dollars. | Must be a number; shown as $
% complete (schedule) | Percent | Enter a percentage, 0–100. | Must be 0–100
Earned value | Calculated | Calculated: [Cost to date] × [% complete (schedule)] ÷ 100 | Formula filled down every row
CPI | Calculated | Calculated: [Earned value] ÷ [Cost to date] | Formula filled down every row
EAC | Calculated | Calculated: [Budget] ÷ [CPI] | Formula filled down every row
VAC | Calculated | Calculated: [EAC] − [Budget] | Formula filled down every row
Guide and worked example |  | https://constructelligence.co/guides/job-cost-forecasting/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Job cost forecasting
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Job | Cost type | Budget | Cost to date | Committed not invoiced | % complete (schedule) | Earned value | CPI | EAC | VAC
J-1104 | Labor | 1337600 | 504000 | 0 | 30
J-1104 | Material | 950400 | 310000 | 82000 | 30