## Instructions
Construction labor forecasting
9 columns · 6 you enter · 0 drop-downs · 3 calculated · 4 validated by type · formulas and checks run 200 rows down
How to use it
1. | Delete the example rows (grey italics) on the Template sheet, or overwrite them.
2. | Fill in the white columns; pick drop-down columns from their lists.
3. | Leave the shaded columns alone — they are formulas, and they fill in as soon as a row has an entry in any of its first three columns.
4. | Use the filter arrows on the header row to sort and filter.
What each column captures
Column | Type | What goes in it | Check
Job | Text | Job number exactly as in your accounting system (e.g. J-1104), so rows join to job cost. | Text
Cost code | Text | Cost code from your cost code list, matching the estimate and the ERP. | Text
Week | Number | Week-ending date. | Must be a number
Budgeted hours | Number | Hours in the estimate for the line. | Must be a number
Installed % | Percent | Enter a percentage, 0–100. | Must be 0–100
Earned hours | Calculated | Calculated: [Budgeted hours] × [Installed %] ÷ 100 | Formula filled down every row
Actual hours | Number | Hours charged to the line from timecards. | Must be a number
Productivity factor | Calculated | Calculated: [Actual hours] ÷ [Earned hours] | Formula filled down every row
Forecast hours at completion | Calculated | Calculated: [Actual hours] + ([Budgeted hours] − [Earned hours]) × [Productivity factor] | Formula filled down every row
Guide and worked example |  | https://constructelligence.co/guides/construction-labor-forecasting/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Construction labor forecasting
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Job | Cost code | Week | Budgeted hours | Installed % | Earned hours | Actual hours | Productivity factor | Forecast hours at completion
J-1104 | 06-110 | 12 | 4614 | 34 |  | 1880