## Instructions
Lien waivers in construction
11 columns · 8 you enter · 2 drop-downs · 1 calculated · 5 validated by type · formulas and checks run 200 rows down
How to use it
1. | Delete the example rows (grey italics) on the Template sheet, or overwrite them.
2. | Fill in the white columns; pick drop-down columns from their lists.
3. | Leave the shaded columns alone — they are formulas, and they fill in as soon as a row has an entry in any of its first three columns.
4. | Use the filter arrows on the header row to sort and filter.
What each column captures
Column | Type | What goes in it | Check
Party | Text | Free text. | Text
Tier | Drop-down | Options: Subcontractor / Supplier / Sub-tier. | Drop-down: Subcontractor / Supplier / Sub-tier
Pay app # | Text | Free text. | Text
Through date | Date | Enter the date. | Must be a date
Amount | Amount ($) | Enter the amount in dollars. | Must be a number; shown as $
Type | Drop-down | Options: Progress / Final. | Drop-down: Progress / Final
Conditional received | Date | Enter the date. | Must be a date
Paid on | Date | Enter the date. | Must be a date
Unconditional received | Date | Enter the date. | Must be a date
Days paid without unconditional | Calculated | Calculated — days since payment with no unconditional waiver on file — chase anything over 14 (= IF(AND([Paid on] ≠ blank, [Unconditional received]=blank), TODAY() − [Paid on], blank)) | Formula filled down every row
Exceptions | Text | Free text. | Text
Guide and worked example |  | https://constructelligence.co/guides/lien-waivers/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Lien waivers in construction
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Party | Tier | Pay app # | Through date | Amount | Type | Conditional received | Paid on | Unconditional received | Days paid without unconditional | Exceptions
Metro Drywall & Supply | Subcontractor | 6 | 2026-08-31 | 48600 | Progress | 2026-09-05 | 2026-09-12 |  |  | Retainage $5,400
Formulas:
Days paid without unconditional = IF(AND([Paid on]<>"",[Unconditional received]=""),TODAY()-[Paid on],"")
Days paid without unconditional = IF(COUNTA([Party]:[Pay app #])=0,"",IF(AND([Paid on]<>"",[Unconditional received]=""),TODAY()-[Paid on],""))