## Instructions
Plumbing software
8 columns · 5 you enter · 0 drop-downs · 3 calculated · 3 validated by type · formulas and checks run 200 rows down
How to use it
1. | Delete the example rows (grey italics) on the Template sheet, or overwrite them.
2. | Fill in the white columns; pick drop-down columns from their lists.
3. | Leave the shaded columns alone — they are formulas, and they fill in as soon as a row has an entry in any of its first three columns.
4. | Use the filter arrows on the header row to sort and filter.
What each column captures
Column | Type | What goes in it | Check
Job | Text | Job number exactly as in your accounting system (e.g. J-1104), so rows join to job cost. | Text
Phase | Text | Phase of the work (e.g. underground, rough-in, trim). | Text
Budgeted hours | Number | Hours in the estimate for the line. | Must be a number
% complete | Percent | Physical percent complete, 0–100, from the field — not cost spent. | Must be 0–100
Earned hours | Calculated | Calculated: [Budgeted hours] × [% complete] ÷ 100 | Formula filled down every row
Actual hours | Number | Hours charged to the line from timecards. | Must be a number
Factor | Calculated | Calculated: [Actual hours] ÷ [Earned hours] | Formula filled down every row
Forecast hours | Calculated | Calculated: [Budgeted hours] × [Factor] | Formula filled down every row
Guide and worked example |  | https://constructelligence.co/software/plumbing-contractors/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Plumbing software
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Job | Phase | Budgeted hours | % complete | Earned hours | Actual hours | Factor | Forecast hours
J-1104 | Rough-in