## Instructions
Punch list template
A punch list: every incomplete or defective item before handover, with location, trade, priority, who it is assigned to, due date, status, who verified it closed, and days open.
15 columns · 11 you enter · 2 drop-downs · 2 calculated · 3 validated by type · formulas and checks run 200 rows down
How to use it
1. | Walk the area and add one row per item, with a location someone else could find and a photo reference.
2. | Assign each item to a trade and a person, with a due date.
3. | Trades set Status to 'Ready for review' when done; only the verifier sets 'Closed' (or 'Rejected').
4. | Filter Overdue and Priority = High each morning; Days open shows what is stuck.
5. | Send each trade its own filtered list rather than the whole sheet.
What each column captures
Column | Type | What goes in it | Check
No. | Text | Item number, so it can be referred to on site and in emails. | Text
Location | Text | Floor, room or gridline — specific enough to walk to. | Text
Trade | Text | The trade responsible for the fix. | Text
Description | Text | What is wrong and what 'fixed' looks like. | Text
Priority | Drop-down | Options: High / Medium / Low. | Drop-down: High / Medium / Low
Photo ref | Text | Photo file name or link. | Text
Identified by | Text | Who found it (architect, owner, superintendent). | Text
Date identified | Date | Enter the date. | Must be a date
Assigned to | Text | The person at the trade who will fix it. | Text
Due date | Date | Enter the date. | Must be a date
Status | Drop-down | Where the item stands; pick from the list so the log can be filtered and counted. Options: Open / In progress / Ready for review / Closed / Rejected. | Drop-down: Open / In progress / Ready for review / Closed / Rejected
Date completed | Date | Enter the date. | Must be a date
Verified by | Text | Who checked it and closed it — not the trade that fixed it. | Text
Days open | Calculated | Calculated — days since the item was raised, until it is completed or answered; counts up daily while open (= IF([Date identified]=blank, blank, IF([Date completed]=blank, TODAY(), [Date completed]) − [Date identified])) | Formula filled down every row
Overdue | Calculated | Calculated — shows 'Overdue' when the due date has passed and the item is still open (= IF(AND([Date completed]=blank, [Due date] ≠ blank, TODAY()>[Due date]), "Overdue", blank)) | Formula filled down every row
Guide and worked example |  | https://constructelligence.co/templates/punch-list-template/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Punch list template
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
No. | Location | Trade | Description | Priority | Photo ref | Identified by | Date identified | Assigned to | Due date | Status | Date completed | Verified by | Days open | Overdue
1 | Room 112, east wall | Painting | Touch up scuffs at 4 ft height | Low | IMG_2031 | Superintendent | 2026-09-21 | R. Diaz (Brightline Painting) | 2026-09-28 | Closed | 2026-09-25 | Superintendent
2 | Room 118 | Electrical | Missing cover plate at receptacle by door | Medium | IMG_2044 | Architect | 2026-09-21 | J. Park (Voltline Electric) | 2026-09-30 | Ready for review
3 | Corridor 1B | Doors & hardware | Door 1B-04 does not latch (rated door) | High | IMG_2050 | Superintendent | 2026-09-22 | K. Moss (Summit Doors) | 2026-09-24 | In progress
4 | Restroom 105 | Plumbing | Lavatory P-trap leaking | High | IMG_2057 | Owner | 2026-09-23 | T. Shaw (Eastline Plumbing) | 2026-09-25 | Open
Formulas:
Days open = IF([Date identified]="","",IF([Date completed]="",TODAY(),[Date completed])-[Date identified])
Days open = IF(COUNTA([No.]:[Trade])=0,"",IF([Date identified]="","",IF([Date completed]="",TODAY(),[Date completed])-[Date identified]))
Overdue = IF(AND([Date completed]="",[Due date]<>"",TODAY()>[Due date]),"Overdue","")
Overdue = IF(COUNTA([No.]:[Trade])=0,"",IF(AND([Date completed]="",[Due date]<>"",TODAY()>[Due date]),"Overdue",""))