## Instructions
RFI template
An RFI log and form: each request for information with the question, the drawing or spec reference, a proposed solution, who it went to, when a response is due, cost and schedule impact, the answer and days open.
16 columns · 11 you enter · 3 drop-downs · 2 calculated · 3 validated by type · formulas and checks run 200 rows down
How to use it
1. | One question per RFI. Reference the sheet or spec section and attach a marked-up snip.
2. | Propose a solution — 'confirm we may use detail 4/A-502 here' gets answered faster than an open question.
3. | Set Response due from the contract's turnaround time or the date the work needs it.
4. | Mark Cost impact and Schedule impact 'Yes' or 'TBD' when they might apply — that is your notice.
5. | Filter Overdue each week and chase; when answered, record the answer and date and check whether it is a change.
What each column captures
Column | Type | What goes in it | Check
RFI no. | Text | Sequential RFI number. | Text
Date sent | Date | Enter the date. | Must be a date
Subject | Text | A few words someone could search for later. | Text
Question | Text | One question per RFI, specific and answerable. | Text
Drawing / spec ref | Text | The sheet, detail or spec section the question is about. | Text
Proposed solution | Text | Your suggested answer — it gets RFIs answered faster. | Text
From | Text | Who is asking. | Text
To | Text | Who has to answer (architect, engineer, owner). | Text
Response due | Date | Date the answer is needed by, from the contract's RFI turnaround or the schedule. | Must be a date
Cost impact | Drop-down | Options: Yes / No / TBD. | Drop-down: Yes / No / TBD
Schedule impact | Drop-down | Options: Yes / No / TBD. | Drop-down: Yes / No / TBD
Status | Drop-down | Where the item stands; pick from the list so the log can be filtered and counted. Options: Open / Answered / Closed / Void. | Drop-down: Open / Answered / Closed / Void
Date answered | Date | Enter the date. | Must be a date
Answer | Text | The response, quoted exactly. | Text
Days open | Calculated | Calculated — days since the item was raised, until it is completed or answered; counts up daily while open (= IF([Date sent]=blank, blank, IF([Date answered]=blank, TODAY(), [Date answered]) − [Date sent])) | Formula filled down every row
Overdue | Calculated | Calculated — shows 'Overdue' when the due date has passed and the item is still open (= IF(AND([Date answered]=blank, [Response due] ≠ blank, TODAY()>[Response due]), "Overdue", blank)) | Formula filled down every row
Guide and worked example |  | https://constructelligence.co/templates/rfi-template/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
RFI template
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
RFI no. | Date sent | Subject | Question | Drawing / spec ref | Proposed solution | From | To | Response due | Cost impact | Schedule impact | Status | Date answered | Answer | Days open | Overdue
31 | 2026-10-02 | Wall chase depth, restrooms 201–204 | Chase on A-501 is 6 in.; P-201 carriers need 8 in. Which governs? | A-501 det. 7; P-201; 22 42 00 | Move wall line 2 in. into corridor (6'-0" clear maintained) | Cobalt Builders | Architect | 2026-10-09 | TBD | Yes | Open
30 | 2026-09-28 | Door 1B-04 hardware set | Hardware set HW-6 lists a closer; door is a pair. Confirm coordinator required. | A-801; 08 71 00 | Add coordinator and flush bolts per HW-7 | Cobalt Builders | Architect | 2026-10-05 | Yes | No | Answered | 2026-10-01 | Confirmed: use HW-7 at 1B-04.
Formulas:
Days open = IF([Date sent]="","",IF([Date answered]="",TODAY(),[Date answered])-[Date sent])
Days open = IF(COUNTA([RFI no.]:[Subject])=0,"",IF([Date sent]="","",IF([Date answered]="",TODAY(),[Date answered])-[Date sent]))
Overdue = IF(AND([Date answered]="",[Response due]<>"",TODAY()>[Response due]),"Overdue","")
Overdue = IF(COUNTA([RFI no.]:[Subject])=0,"",IF(AND([Date answered]="",[Response due]<>"",TODAY()>[Response due]),"Overdue",""))