## Instructions
AI for construction scheduling and project management
10 columns · 9 you enter · 1 drop-downs · 0 calculated · 4 validated by type · formulas and checks run 200 rows down
How to use it
1. | Delete the example rows (grey italics) on the Template sheet, or overwrite them.
2. | Fill in the white columns; pick drop-down columns from their lists.
3. | Leave the shaded columns alone — they are formulas, and they fill in as soon as a row has an entry in any of its first three columns.
4. | Use the filter arrows on the header row to sort and filter.
What each column captures
Column | Type | What goes in it | Check
Activity ID | Text | Free text. | Text
Activity | Text | The schedule activity or scope of work. | Text
On critical path? | Drop-down | Options: Yes / No. | Drop-down: Yes / No
Remaining duration (d) | Number | Enter a number. | Must be a number
Chance of slip % | Percent | Enter a percentage, 0–100. | Must be 0–100
Likely slip (d) | Number | Enter a number. | Must be a number
Driver | Text | Free text. | Text
Cost per day of slip | Amount ($) | Enter the amount in dollars. | Must be a number; shown as $
Mitigation | Text | Free text. | Text
Owner | Text | The person responsible for the row. | Text
Guide and worked example |  | https://constructelligence.co/guides/ai-construction-scheduling/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
AI for construction scheduling and project management
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Activity ID | Activity | On critical path? | Remaining duration (d) | Chance of slip % | Likely slip (d) | Driver | Cost per day of slip | Mitigation | Owner
A1040 | Curtain wall | Yes | 25