## Instructions
Construction scope of work template
A scope of work as a table: one row per scope item, each marked included, excluded, by others, allowance or alternate, with quantities, location, drawing reference and how it will be accepted.
12 columns · 11 you enter · 1 drop-downs · 0 calculated · 2 validated by type · formulas and checks run 200 rows down
How to use it
1. | List every scope item from the drawings and specs, one per row — including what you are NOT doing.
2. | Mark each row's Inclusion; anything 'By others' names the trade that carries it.
3. | Add quantities where the item is measurable, and the sheet or spec section that defines it.
4. | Write acceptance criteria for anything that will be inspected (finish levels, tests, tolerances).
5. | Attach the sheet to the subcontract or proposal as the scope exhibit, and filter by Inclusion to read it back.
What each column captures
Column | Type | What goes in it | Check
Item | Text | Line number, so the row can be referred to. | Text
CSI section | Text | MasterFormat section number (e.g. 09 21 16) so the scope lines up with the specs. | Text
Scope item | Text | The work, described specifically enough to price and to inspect. | Text
Inclusion | Drop-down | Whether the item is in this contract — and if not, whose it is. Options: Included / Excluded / By others / Allowance / Alternate. | Drop-down: Included / Excluded / By others / Allowance / Alternate
Quantity | Number | Enter a number. | Must be a number
Unit | Text | Unit of measure (EA, LF, SF, CY, HR, LS). | Text
Location / area | Text | Where on the project the item applies. | Text
Drawing / spec ref | Text | Sheet and spec section that define the item. | Text
Responsible party | Text | The company that performs it (for 'By others', the trade that does). | Text
Acceptance criteria | Text | How the item will be inspected and accepted as complete. | Text
Allowance amount ($) | Amount ($) | For allowance items, the amount carried; reconciled against actual cost. | Must be a number; shown as $
Notes | Text | Anything that explains the row; free text. | Text
Guide and worked example |  | https://constructelligence.co/templates/scope-of-work-template/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
Construction scope of work template
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Item | CSI section | Scope item | Inclusion | Quantity | Unit | Location / area | Drawing / spec ref | Responsible party | Acceptance criteria | Allowance amount ($) | Notes
1 | 09 21 16 | Gypsum board partitions to 10'-0" incl. framing | Included | 14200 | SF | Floors 1–2 | A-501 / 09 21 16 | Metro Interiors | Level 4 finish; inspected before taping
2 | 09 21 16 | Level 5 finish at lobby feature wall | Included | 820 | SF | Lobby | A-601 | Metro Interiors | Level 5 under raking light
3 | 07 84 00 | Firestopping at rated wall penetrations | By others |  |  | All rated walls | A-502 | Each MEP trade | UL system per penetration |  | Each trade firestops its own penetrations
4 | 09 51 00 | Acoustical ceilings | Excluded |  |  |  |  | Ceiling contractor |  |  | Separate subcontract
5 | 05 40 00 | Framing above 10'-0" at floor 2 corridor | Alternate | 2600 | SF | Floor 2 corridor | A-501 | Metro Interiors |  |  | Add alternate 1
6 | 06 10 00 | Blocking for casework and grab bars | Allowance | 1 | LS | Exam rooms | A-701 | Metro Interiors | Blocking in place before board | 6500 | Reconcile against actual