## Instructions
The three-week look-ahead schedule
10 columns · 9 you enter · 1 drop-downs · 0 calculated · 2 validated by type · formulas and checks run 200 rows down
How to use it
1. | Delete the example rows (grey italics) on the Template sheet, or overwrite them.
2. | Fill in the white columns; pick drop-down columns from their lists.
3. | Leave the shaded columns alone — they are formulas, and they fill in as soon as a row has an entry in any of its first three columns.
4. | Use the filter arrows on the header row to sort and filter.
What each column captures
Column | Type | What goes in it | Check
Task | Text | Free text. | Text
Trade / crew | Text | Free text. | Text
Area | Text | Free text. | Text
Start | Date | Enter the date. | Must be a date
Finish | Date | Enter the date. | Must be a date
Constraint | Text | Free text. | Text
Constraint owner | Text | Free text. | Text
Clear by | Text | Free text. | Text
Done as planned (Y/N) | Drop-down | Options: Y / N. | Drop-down: Y / N
Reason if missed | Text | Free text. | Text
Guide and worked example |  | https://constructelligence.co/guides/three-week-look-ahead-schedule/
Free template from Constructelligence — constructelligence.co. Use, copy and adapt freely.

## Template
The three-week look-ahead schedule
White columns: you enter · drop-down columns: pick from the list · shaded columns: calculated · grey italic rows are examples — overwrite them
Totals (filtered rows)
Task | Trade / crew | Area | Start | Finish | Constraint | Constraint owner | Clear by | Done as planned (Y/N) | Reason if missed
Hang board L3 east | Drywall | L3-E |  |  | Board delivery | Drywall sub